## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog
| Table 1 | Product Backlog
Sprint Backlog
| Table 1 | Sprint Backlog
Stand up Meeting
| Table 1 | Stand up Meeting
Retrospection
| Table 1 | Retrospection

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-008 | Environment setup and library installation | MUST HAVE |  | Praveen | 3- Completed
S1 | S1 | US-008 | Fetch market news using Google News RSS | MUST HAVE |  | Praveen | 3- Completed
S1 | S1 | US-008 | Generate/ingest mock social sentiment data | SHOULD HAVE |  | Praveen | 3- Completed
S1 | S1 | US-008 | Combine news + social data into unified corpus | MUST HAVE |  | Praveen | 3- Completed
S1 | S1 | US-008 | Clean and standardize timestamps across data | MUST HAVE |  | Praveen | 3- Completed
S2 | S2 | US-008 | Build Gemini LLM sentiment classification module | MUST HAVE |  | Praveen | 3- Completed
S2 | S2 | US-008 | Integrate Hugging Face Model FinBert for sentiment analysis | MUST HAVE |  | Praveen | 3- Completed
S2 | S2 | US-008 | Compute aggregate sentiment scores and ratios | MUST HAVE |  | Praveen | 3- Completed
S2 | S2 | US-008 | Generate strategic insights using LLM | MUST HAVE |  | Praveen | 3- Completed
S2 | S2 | US-008 | Implement LLM error handling and fallbacks | SHOULD HAVE |  | Praveen | 3- Completed
S2 | S2 | US-008 | Convert sentiment JSON into DataFrame | SHOULD HAVE |  | Praveen | 3- Completed
S2 | S2 | US-008 | Created a Sample Dashboard to be Enhanced Later | MUST HAVE |  | Praveen | 3- Completed
S3 | S3 | US-008 | Test all the edge cases and make the code error free | MUST HAVE |  | Praveen | 3- Completed
S3 | S3 | US-008 | Download historical stock prices via yfinance | MUST HAVE |  | Praveen | 3- Completed
S3 | S3 | US-008 | Create ARIMA/Prophet 7-day forecast model | MUST HAVE |  | Praveen | 3- Completed
S3 | S3 | US-008 | Generate BUY/SELL/HOLD signal from forecast | MUST HAVE |  | Praveen | 3- Completed
S3 | S3 | US-008 | Develop Slack alert webhook module | SHOULD HAVE |  | Praveen | 3- Completed
S3 | S3 | US-008 | Send alerts with forecast + sentiment summary | MUST HAVE |  | Praveen | 3- Completed
S4 | S4 | US-008 | Fetch company metadata (CEO, revenue, HQ) | SHOULD HAVE |  | Praveen | 3- Completed
S4 | S4 | US-008 | Fetch competitor fundamentals for comparison | MUST HAVE |  | Praveen | 3- Completed
S4 | S4 | US-008 | Plot historical vs forecasted price chart | MUST HAVE |  | Praveen | 3- Completed
S4 | S4 | US-008 | Build competitor comparison charts | MUST HAVE |  | Praveen | 3- Completed
S4 | S4 | US-008 | Generate LLM-based strategic commentary | SHOULD HAVE |  | Praveen | 3- Completed
S4 | S4 | US-008 | Build final interactive dashboard (Plotly) | MUST HAVE |  | Praveen | 3- Completed
Note on F1: Imported Author: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 31 | 2.5 | 5 | 8 | 3.5 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-008 | 1 | Environment setup and library installation | 3/11/25 | 3/11/25 |  | Build | 3- Completed | 1 | bar: Day 1
US-008 | 2 | Fetch market news using Google News RSS | 4/11/25 | 6/11/25 |  | Coding | 3- Completed | 3 | bar: Day 1 to Day 3
US-008 | 3 | Generate/ingest mock social sentiment data | 4/11/25 | 6/11/25 |  | Coding | 3- Completed | 3 | Day 1: 0; Day 2: 1; Day 3: 2
US-008 | 4 | Combine news + social data into unified corpus | 4/11/25 | 6/11/25 |  | Coding | 3- Completed | 3 | Day 1: 0; Day 2: 1.5; Day 3: 1.5
US-008 | 5 | Clean and standardize timestamps across data | 4/11/25 | 7/11/25 |  | Coding | 3- Completed | 4 | Day 1: 0; Day 2: 1; Day 3: 1.5; Day 4: 1.5
US-008 | 6 | Download historical stock prices via yfinance | 4/11/25 | 7/11/25 |  | Coding | 3- Completed | 3 | Day 1: 0.5; Day 2: 0.5; Day 3: 1; Day 4: 1
US-008 | 7 | Test all the edge cases and make the code error free | 4/11/25 | 8/11/25 |  | Unit Test | 3- Completed | 4 | Day 1: 0; Day 2: 0; Day 3: 1; Day 4: 1; Day 5: 2
US-008 | 8 | Plot Sentiment Distribution | 4/11/25 | 9/11/23 |  | Design | 3- Completed | 2 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0.5; Day 6: 1.5
US-008 | 9 | Plot Closing Price | 4/11/25 | 9/11/24 |  | Design | 3- Completed | 3 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 1.5; Day 6: 1.5
US-008 | 10 | Created a Sample Dashboard to be Enhanced Later | 4/11/25 | 10/11/25 |  | Design | 3- Completed | 5 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 1; Day 6: 1; Day 7: 3
Note on D2: Imported Author: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on E2: Imported Author: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on I3: Imported Author: This is the total task estimated in hours for all the user stories -Sumeet Kumar Barua08
Note on J3: Imported Author: Pending effort hours after completion of day 1 work -Sumeet Kumar Barua08
Note on K3: Imported Author: Pending effort hours after completion of day 2 work -Sumeet Kumar Barua08
Note on L3: Imported Author: Pending effort hours after completion of day 3 work -Sumeet Kumar Barua08
Note on M3: Imported Author: Pending effort hours after completion of day 4 work -Sumeet Kumar Barua08
Note on N3: Imported Author: Pending effort hours after completion of day 5 work -Sumeet Kumar Barua08
Note on O3: Imported Author: Pending effort hours after completion of day 6 work -Sumeet Kumar Barua08
Note on P3: Imported Author: Pending effort hours after completion of day 7 work -Sumeet Kumar Barua08
Note on Q3: Imported Author: Pending effort hours after completion of day 8 work -Sumeet Kumar Barua08
Note on R3: Imported Author: Pending effort hours after completion of day 9 work -Sumeet Kumar Barua08
Note on S3: Imported Author: Pending effort hours after completion of day 10 work -Sumeet Kumar Barua08
Note on T3: Imported Author: Pending effort hours after completion of day 11 work -Sumeet Kumar Barua08
Note on U3: Imported Author: Pending effort hours after completion of day 12 work -Sumeet Kumar Barua08
Note on V3: Imported Author: Pending effort hours after completion of day 13 work -Sumeet Kumar Barua08
Note on W3: Imported Author: Pending effort hours after completion of day 14 work -Sumeet Kumar Barua08

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7